## Sheet1
Related User Story | Task Description | Initial Estimate(Hour) | Amount Remaining After…
|  |  | Week 1 | Week 2 | Week 3 | Week 4
As a Medical Personnel, I want to view patient information, So that I can get patient's information | Make patient information UI for view | 2 | 1 | 1 | 0 | 0
| Add function that allow medical personnel to search patients with tests | 2 | 2 | 0 | 0 | 0
As a Medical Personnel, I want to niew patient medical conditions in record and history, So that I can give my suggestion and make a medical plan for patient based on history and record | Make medical conditions UI for view | 3 | 2 | 1 | 0 | 0
| Add functions that allow medical personnel give their suggestion with associated UI, and tests | 1 | 1 | 1 | 0 | 0
As a Medical Personnel, I want to add prescription, So that patient can add it for medications | Add functtion that allow maedical personnel to add prescription with associated UI, and tests | 4 | 3 | 3 | 3 | 0
As a Medical Personnel, I want to mange appointments, So that I can deal with conflicting events that may arise | Make appointment view UI | 3 | 3 | 3 | 0 | 0
| Add functions that allow medical personnel to add and remove availabilities with tests | 2 | 2 | 2 | 0 | 0
| Add function that allow medical personnel to cancel an appoitment with tests | 2 | 2 | 0 | 0 | 0
As a Medical Personnel, I want to enter appointment notes, So that patient have ability to view notes that we talk about | Add function that allow medical personnel to enter their notes and feedback with test | 4 | 4 | 4 | 4 | 0
As a Medical Personnel, I want to record vital information for appoinmnet, So that I have a way to view history appointments | Add function that allow medical personnel to view history appointments with assoicated UI and tests | 4 | 4 | 4 | 0 | 0
As a Medical Personnel, I want to add a caregiver for patient, So that we are able to take care of patient | Add funciton that allow medical personnel to add a caregiver for patient | 2 | 2 | 2 | 0 | 0
As a Medical Personnel, I want to remove a caregiver for patient, So that I am able to add a new caregiver for patient | Add funciton that allow medical personnel to remove a caregiver for patient | 2 | 2 | 2 | 0 | 0
| Estimate Totals | 31 | 28 | 23 | 7 | 0