## Sheet1
Related User Story | Task Description | Initial Estimate(Hour) | Amount Remaining After…
|  |  | Week 1 | Week 2 | Week 3 | Week 4
As a Patient, I want to view my self information, So that I can check my information | Make a Dashboard GUI | 1 | 1 | 0 | 0 | 0
As a Patient, I want to manage my general information to record, So that I can keep my general information up-to-date | Make a general information GUI with Patient class and tests | 3 | 2 | 1 | 0 | 0
As a Patient, I want to remove a caregiver for myself, So that I can add a new caregiver | Make a dialog for add and remove caregiver with caregiver class and tests | 3 | 3 | 3 | 3 | 0
As a Patient, I want to add a caregiver for myself, So that I can have caregiver to help me for medical treat | Make a dialog for book and cancel an appointment with Appointment class and tests | 3 | 3 | 3 | 0 | 0
As a Patient, I want to cancel an appointment with Medical personnel, So that I can deal with conflicting events that may arise | Make code behind for update general information | 4 | 4 | 4 | 4 | 0
As a Patient, I want to book an appointment meet with Medical personnel, So that I can meet a Medical personnel for detail information | Make code behind for add and remove caregiver | 4 | 4 | 4 | 0 | 0
| Make code behind for book and cancel appointments | 4 | 4 | 4 | 0 | 0
As a Patient, I want to mange medical conditions in record, So that I can keep tracking my medical conditions | Make dialog for add and remove a new Medical Condition with Medical Condition class and tests | 2 | 2 | 2 | 0 | 0
As a Patient, I want to view my medical conditions in history, So that I can check what medical conditions I have used | Make a Medical conditions GUI | 2 | 2 | 2 | 0 | 0
| Make code behind for add and remove Medical Condition | 4 | 4 | 4 | 4 | 0
As a Patient, I want to mange my medications to record, So that I can update my medical conditions | Make dialog for add and remove a Medication with Medication class and tests | 2 | 2 | 2 | 2 | 0
| Make an Medications GUI | 2 | 2 | 2 | 2 | 0
| Make code behind for add and remove Medication | 4 | 4 | 4 | 4 | 0
| Estimate Totals | 38 | 37 | 35 | 19 | 0